## 0. Overview
SAHAYAK - Citizen Operating System
Hackathon theme | Better Communities, Better Governance
Time budget | 3 hours
Team size | 3 (Person A, Person B, Person C)
Hard constraint | Only free, publicly available APIs. No paid tier, no approval-gated API.
Core idea | One Next.js app + one Gemini key + one Supabase project = 8 modules. Each module is one page + one API route. No separate backend, no second model, no extra service.
Pitch line | Internet ho ya na ho, smartphone ho ya na ho - har citizen tak sarkar pahunchegi.
Golden rules
1 | Deploy to Vercel at the 45 min mark, then keep redeploying. Never leave deploy to the last 10 min.
2 | Every Gemini response gets cached in Dexie. Free tier is 15 req/min - a live demo must not depend on a fresh call.
3 | Every module has hardcoded demo data as fallback. If an API fails on stage, the UI still works.
4 | Person A owns shared components (VoiceInput, SpeakButton, t()). B and C only consume them, never edit them.
5 | Commit and push every 20 min. Small commits, main branch, no feature branches at this time scale.
Sheets in this file
1. Modules | Final 8 modules, what gets built, tech used, owner
2. Person A - Frontend | Full task list for Person A
3. Person B - AI | Full task list for Person B
4. Person C - Backend | Full task list for Person C
5. Timeline | Minute-by-minute 3-hour schedule, all three in parallel
6. Tech Stack | Every library and API with signup link and cost proof
7. API Contracts | Exact route shapes so the three can work without blocking each other
8. Demo Script | 3-minute stage run, step by step

## 1. Modules
# | Module | Problems it solves | What we actually build in 3 hrs | Tech (all free) | Owner | Priority
1 | Scheme & Scholarship Discovery | Doesn't know what exists; confusing eligibility; missed deadlines; fake WhatsApp schemes; agent dependence | 40 schemes in schemes.json; json-logic eligibility match; 'Rs X unclaimed per year' card; '1 document away' suggestion; paste-a-forward fake scheme checker | json-logic-js, Gemini (rule extraction), Supabase | B (logic) + A (UI) | P0 - must work
2 | Document Scan & Auto-Profile | Document chains; name/spelling mismatch rejections; certificate expiry; agent dependence | Camera photo -> Gemini vision -> structured profile (name, DOB, income, category, state); RapidFuzz-style mismatch warning; expiry reminder list | Gemini 2.0 Flash vision, Tesseract.js (offline fallback), Supabase Storage | B (extract) + A (camera UI) | P0 - must work
3 | Form Helper + Rejection Decoder | Jargon; complex forms; rejection with no reason; repeated office visits | Voice Q&A in Hindi fills a real PDF form via pdf-lib; 'Why is this field asked?' tooltip; 'Explain my rejection' - paste text/screenshot, get cause + fix steps | Web Speech API, pdf-lib, Gemini | A (voice flow) + B (prompts) | P0 - must work
4 | Civic Complaints + Escalation | Where to complain; fake closures; no tracking; no escalation; fear of retaliation | Photo + GPS -> Gemini classifies issue & severity -> Nominatim gives ward -> Supabase row -> status timeline; auto-escalation letter draft; RTI application draft; anonymous mode toggle; map pins | Gemini vision, Nominatim (OSM), MapLibre GL, Supabase, PostGIS | C (routing/DB) + B (drafts) | P0 - must work
5 | Multilingual & Voice-First Access | English/Hindi only; low literacy; disability; info never reaches people | 8 language switcher (Gemini translate, cached in Dexie); voice input + audio output on every screen; audio circular explainer ('what changed, who it affects, what to do') | Web Speech API, SpeechSynthesis API, Gemini translate, Dexie cache | A (owner) + B (translate route) | P0 - the differentiator
6 | Transparency & Accountability Dashboard | Benefits stop with no reason; bribes; no feedback loop; leakage | Recharts dashboard: complaints per ward, median resolution time, repeat-problem hotspots; anonymous office scorecard (time taken / bribe asked); policy simulator slider (income limit -> newly eligible count) | Recharts, Supabase aggregate queries | C | P1 - build after P0
7 | Transportation Ease | How to reach the office; travel cost & lost wages; bus pass queues; no transport complaint channel | OSRM route from user to the office a scheme needs (time + cost + steps); 'Ek din, saare kaam' planner (Gemini orders pending tasks into one trip); Ed25519 signed QR bus pass that verifies offline | OSRM demo server, MapLibre, Gemini, @noble/ed25519, qrcode | C (routing) + A (QR UI) | P1 - build after P0
8 | Offline + Online (Phygital) Layer | No internet; feature phones; shared phones; village kiosks | PWA installable; all screens cached (Workbox); Dexie offline write queue with auto-sync on reconnect; offline OCR via Tesseract.js; offline QR verification; kiosk mode (big-button layout) | next-pwa, Workbox, Dexie.js, Tesseract.js | A | P0 - airplane mode demo

## 2. Person A - Frontend
PERSON A - FRONTEND, VOICE & OFFLINE
Owns: the app shell, every shared component, language switching, voice, PWA and offline sync. B and C import your components - do not let them rewrite them.
Slot | Task | Deliverable (definition of done) | Files / routes to touch | Module | Depends on
0:00-0:15 | Scaffold the app and push the first commit | create-next-app runs, deps installed, repo pushed, Vercel project linked and a blank page is live on a URL | repo root, package.json | Core | Nothing - you start first
0:15-0:30 | App shell + bottom navigation for 8 modules | 8 tabs (Home, Schemes, Scan, Form, Complaint, Transport, Dashboard, Settings) route correctly on mobile width | app/layout.tsx, components/BottomNav.tsx | Core | -
0:30-0:45 | Shared components: <VoiceInput>, <SpeakButton>, <BigButton>, <CameraInput> | VoiceInput returns a transcript string in the chosen language; SpeakButton reads any text aloud; both exported and documented in a one-line comment | components/voice/*.tsx | M5 | -
0:45-1:00 | Language switcher + t() hook with Dexie cache | 8 languages (hi, en, ta, bn, mr, te, kn, or) switch live; translations fetched once from /api/translate then served from cache | lib/i18n.ts, components/LangSwitch.tsx | M5 | B's /api/translate
1:00-1:20 | Document scan screen | Camera or file input -> POST to /api/extract -> profile fields shown in editable cards -> saved to Supabase and Dexie | app/scan/page.tsx | M2 | B's /api/extract
1:20-1:45 | Voice form-fill screen | App asks each field aloud, user answers by voice, answers land in a real PDF via pdf-lib, user downloads the filled form | app/form/page.tsx, lib/pdf.ts | M3 | B's /api/form-fields
1:45-2:05 | PWA + offline write queue | App installable; works with network off; writes queue in Dexie and flush automatically on reconnect with a visible sync badge | next.config.js (next-pwa), lib/offline.ts, components/SyncBadge.tsx | M8 | C's Supabase schema
2:05-2:20 | Offline OCR + offline QR verify + kiosk mode | With network off, Tesseract.js reads a document photo; QR pass scans and verifies via public key; kiosk layout (huge buttons, no text input) behind ?kiosk=1 | lib/ocr-offline.ts, app/verify/page.tsx | M8, M7 | C's QR signing route
2:20-2:40 | Polish pass across all screens | Loading skeletons, empty states, error toasts, Hindi labels everywhere, works on a real phone in Chrome | all pages | All | B and C features merged
2:40-3:00 | Final deploy + airplane-mode rehearsal | Production URL works on the demo phone; the airplane-mode -> sync flow is rehearsed twice without a failure | Vercel | M8 | Everything merged

## 3. Person B - AI
PERSON B - AI, PROMPTS & SCHEME LOGIC
Owns: every Gemini call and every piece of eligibility logic. All model calls live in lib/gemini.ts - nobody else calls the API directly. Each route must return the documented JSON even when the model fails (fallback to canned demo data).
Slot | Task | Deliverable (definition of done) | Files / routes to touch | Module | Depends on
0:00-0:10 | Get the Gemini key and prove it works | GEMINI_API_KEY in .env.local and on Vercel; a curl/test script returns text and reads an image | .env.local, scripts/test-gemini.ts | Core | Nothing
0:10-0:25 | lib/gemini.ts - one wrapper, JSON mode, retry, Groq fallback | A single callModel(prompt, image?, schema) helper with 1 retry, 8s timeout, and a Groq fallback on 429 | lib/gemini.ts | Core | -
0:25-0:50 | /api/extract - document photo to structured profile | Returns {name, dob, gender, income, category, state, district, docType, expiryDate, confidence} plus a mismatch[] array comparing against the saved profile | app/api/extract/route.ts | M2 | -
0:50-1:10 | schemes.json - 40 schemes with machine-readable rules | Each entry: id, name, dept, benefitAmount, docsRequired[], applyUrl, officeType, and a json-logic rule object. Use Gemini to draft, then eyeball every rule by hand | data/schemes.json | M1 | -
1:10-1:30 | Eligibility engine + unclaimed value + 'one document away' | matchSchemes(profile) returns {eligible[], nearMiss[], totalUnclaimed}. nearMiss says exactly which single document unlocks which schemes | lib/eligibility.ts, app/api/match/route.ts | M1 | schemes.json
1:30-1:45 | /api/translate + /api/simplify + /api/explain-field | Translate any string array into a target language; rewrite government jargon at a 5th-grade reading level; explain why a form field is asked and the common rejection reason | app/api/translate/route.ts, app/api/simplify/route.ts | M5, M3 | -
1:45-2:00 | /api/classify-issue - civic photo to category | Returns {category, severity, department, suggestedTitle, description} for a pothole/garbage/streetlight/waterlogging photo | app/api/classify/route.ts | M4 | -
2:00-2:15 | /api/draft - complaint, escalation and RTI letters | Given a complaint row and a stage (first ¦ escalation ¦ rti), returns a properly formatted letter in the user's language, ready to print or send | app/api/draft/route.ts | M4 | C's complaint schema
2:15-2:30 | /api/explain-rejection + /api/day-plan | Rejection: paste text or a screenshot, get cause + numbered fix steps. Day plan: given pending tasks, return one ordered single-trip itinerary | app/api/explain-rejection/route.ts, app/api/day-plan/route.ts | M3, M7 | C's OSRM route data
2:30-2:45 | Fake-scheme checker + response cache seeding | Paste a WhatsApp forward -> Real / Fake verdict with the official source link. All demo prompts pre-warmed into the cache so the stage demo needs no live call | app/api/verify-message/route.ts, scripts/seed-cache.ts | M1 | -
2:45-3:00 | Prompt QA with the real demo inputs | Every route tested with the exact demo document, photo and text; outputs are stable across 3 runs | all routes | All | Final build

## 4. Person C - Backend
PERSON C - DATA, MAPS, TRANSPORT & DASHBOARD
Owns: Supabase schema, all geo and routing work, the transparency dashboard and the signed QR system. Ship the schema in the first 20 minutes - A and B are both blocked on it.
Slot | Task | Deliverable (definition of done) | Files / routes to touch | Module | Depends on
0:00-0:20 | Supabase project + schema + RLS (ship this first) | Tables profiles, documents, schemes_saved, complaints, complaint_events, ratings, passes created; anon insert policies on; connection string shared with A and B | supabase/schema.sql, lib/supabase.ts | Core | Nothing - everyone waits on you
0:20-0:35 | Seed data + demo rows | One demo profile, 12 complaints spread over 4 wards with timestamps, 20 ratings - enough to make the dashboard look alive | supabase/seed.sql | M6 | schema
0:35-0:55 | Map screen with MapLibre + OSM | Complaint pins render on an OSM basemap, click a pin to see the issue card; user location dot works | components/Map.tsx, app/complaint/page.tsx | M4 | seed data
0:55-1:15 | Complaint submit flow: GPS + Nominatim ward routing | POST /api/complaint stores photo URL, lat/lng, ward and department from Nominatim reverse geocode, and writes the first complaint_event; hardcoded fallback ward if Nominatim rate-limits | app/api/complaint/route.ts, lib/geo.ts | M4 | B's /api/classify
1:15-1:30 | Status timeline + auto-escalation timer | Complaint page shows a timeline; a 'days elapsed' check exposes an Escalate button that calls B's /api/draft, and a Resolve step that needs an after-photo | app/complaint/[id]/page.tsx | M4 | B's /api/draft
1:30-1:50 | Transport: OSRM route to the office a scheme needs | Given user location and an office, return distance, duration, approximate fare and step list; render the route line on the map; cached fallback route for the demo | app/api/route/route.ts, lib/osrm.ts | M7 | map
1:50-2:05 | Signed QR pass / eligibility slip | Ed25519 keypair in env; /api/pass signs {name, scheme, validTill} and returns a QR; A's verify page validates it with the public key while offline | app/api/pass/route.ts, lib/sign.ts | M7, M8 | -
2:05-2:30 | Transparency dashboard | Recharts page: complaints per ward (bar), median resolution days (line), category split (pie), repeat-hotspot table - all from live Supabase queries | app/dashboard/page.tsx, lib/stats.ts | M6 | seed data
2:30-2:45 | Office scorecard + policy simulator | Anonymous rating form (wait time, bribe asked y/n) writes to ratings and shows a per-office score; a slider changes the income limit and recomputes how many seeded profiles become eligible | app/dashboard/scorecard/page.tsx | M6 | B's eligibility engine
2:45-3:00 | Data sanity check for the demo | Every chart has data, no empty states on stage, the demo complaint exists in the right ward, QR verifies offline | Supabase | All | Final build

## 5. Timeline
Time | Person A - Frontend/Voice/Offline | Person B - AI/Prompts/Logic | Person C - Data/Maps/Dashboard | Checkpoint
0:00-0:20 | Scaffold Next.js, push repo, link Vercel | Gemini key + lib/gemini.ts wrapper | Supabase schema + RLS + share creds | Repo live on Vercel, schema shared
0:20-0:45 | App shell, 8-tab nav, shared voice components | /api/extract working on a real document photo | Seed data + MapLibre map with pins | Blank-but-navigable app deployed
0:45-1:10 | Language switcher + t() with cache | schemes.json 40 entries with json-logic rules | Complaint submit + Nominatim ward routing | DEPLOY #2
1:10-1:35 | Scan screen wired to /api/extract | Eligibility engine + unclaimed value | Status timeline + escalation button | Scan -> profile works end to end
1:35-2:00 | Voice form-fill -> filled PDF download | translate / simplify / classify routes | OSRM transport route + signed QR pass | DEPLOY #3 - P0 modules all alive
2:00-2:20 | PWA + Dexie offline queue + sync badge | draft letters, rejection decoder, day plan | Recharts dashboard from live data | Airplane-mode test passes
2:20-2:40 | Offline OCR, offline QR verify, kiosk mode, polish | Fake-scheme checker + cache seeding | Scorecard + policy simulator | DEPLOY #4 - feature freeze
2:40-3:00 | Final deploy + rehearse on the demo phone | Prompt QA on exact demo inputs | Data sanity check, no empty charts | Two clean rehearsals done

## 6. Tech Stack
Layer | Choice | Why this one | Free / public? | Where to get it | Owner
App framework | Next.js 14 (App Router) + TypeScript | Frontend and API routes in one deploy - no separate backend to host | Open source | npx create-next-app@latest | A
Styling / UI | Tailwind CSS + shadcn/ui + lucide-react | Accessible components with no design time | Open source | ui.shadcn.com | A
LLM + Vision + Translate | Google Gemini 2.0 Flash | Free tier with no card, vision and JSON mode included, 22 Indian languages | FREE - 15 req/min, 1500/day | aistudio.google.com/apikey | B
LLM fallback | Groq - Llama 3.3 70B | Takes over when Gemini hits a rate limit mid-demo | FREE tier | console.groq.com | B
Speech to text | Web Speech API (browser) | Zero setup, zero cost, supports hi-IN / ta-IN / bn-IN and more | FREE - built into Chrome | Browser native | A
Text to speech | SpeechSynthesis API (browser) | Audio output for non-readers with no API call | FREE - built into Chrome | Browser native | A
Offline OCR | Tesseract.js | Runs in the browser so the airplane-mode demo still reads documents | Open source | npm i tesseract.js | A
Database + Storage + Auth | Supabase (Postgres + PostGIS) | Free Postgres, file storage, phone OTP and row level security in one project | FREE - 500MB | supabase.com | C
Maps | MapLibre GL JS + OpenStreetMap tiles | No token, no billing, unlike Google Maps and Mapbox | FREE / open | maplibre.org | C
Geocoding / ward lookup | Nominatim (OSM) | Reverse geocode lat/lng to ward and district | FREE - 1 req/sec, set a User-Agent | nominatim.openstreetmap.org | C
Routing / transport | OSRM demo server | Distance, duration and steps to the government office | FREE public demo server | router.project-osrm.org | C
Eligibility rules | json-logic-js | Deterministic eligibility - the model must never decide who qualifies | Open source | npm i json-logic-js | B
PDF fill | pdf-lib | Writes answers onto a real government PDF, all client-side | Open source | npm i pdf-lib | A
Charts | Recharts | Dashboard in minutes with React components | Open source | npm i recharts | C
Offline cache | next-pwa (Workbox) | Installable app, all screens cached | Open source | npm i next-pwa | A
Local database | Dexie.js (IndexedDB) | Offline write queue plus the Gemini response cache | Open source | npm i dexie | A
Signed QR | @noble/ed25519 + qrcode | A bus pass or eligibility slip that verifies with no internet | Open source | npm i @noble/ed25519 qrcode | C
Hosting | Vercel | Push to main and it deploys; free HTTPS URL for the demo phone | FREE hobby tier | vercel.com | A
Scheme data | Static schemes.json, drafted from myScheme.gov.in | No scraper to debug and no rate limit on stage | FREE - public info | myscheme.gov.in | B
AVOID | Bhashini, DigiLocker/API Setu, WhatsApp Cloud API, Twilio, Exotel, Neo4j, YOLO training | Signup approval, business verification, KYC or paid - all fatal inside 3 hours | NOT usable today | Put these on the roadmap slide instead | -

## 7. API Contracts
Route | Method | Request body | Response (lock this shape at 0:20) | Owner | Consumed by
/api/extract | POST | { imageBase64 } | { name, dob, gender, income, category, state, district, docType, expiryDate, confidence, mismatch[] } | B | A - scan screen
/api/match | POST | { profile } | { eligible[{id,name,benefitAmount,docsRequired[],applyUrl,officeType}], nearMiss[{schemeId,missingDoc}], totalUnclaimed } | B | A - schemes screen
/api/translate | POST | { strings[], targetLang } | { translations[] } | B | A - i18n hook
/api/simplify | POST | { text, lang } | { simplified, glossary[{term,meaning}] } | B | A - any jargon block
/api/explain-field | POST | { fieldLabel, formName, lang } | { why, commonMistake, example } | B | A - form screen
/api/classify | POST | { imageBase64, lat, lng } | { category, severity, department, suggestedTitle, description } | B | C - complaint submit
/api/draft | POST | { complaintId, stage: first¦escalation¦rti, lang } | { subject, body, sendTo } | B | C - complaint timeline
/api/explain-rejection | POST | { text ¦ imageBase64, lang } | { cause, steps[], docsNeeded[] } | B | A - form screen
/api/day-plan | POST | { tasks[], userLocation } | { ordered[{task,office,arriveBy,travel}], totalHours, totalFare } | B | C - transport screen
/api/verify-message | POST | { text } | { verdict: real¦fake¦unclear, reason, officialUrl } | B | A - home screen
/api/complaint | POST | { imageUrl, lat, lng, category, description, anonymous } | { id, ward, department, status, createdAt } | C | A - complaint screen
/api/complaint/[id] | GET | - | { complaint, events[{stage,at,note}], canEscalate } | C | A - timeline
/api/route | POST | { fromLat, fromLng, officeId } | { distanceKm, durationMin, fareApprox, steps[], geometry } | C | A - transport screen
/api/pass | POST | { name, scheme, validTill } | { qrDataUrl, signature, publicKey } | C | A - QR + verify page
/api/stats | GET | ?ward= | { perWard[], medianResolveDays, categorySplit[], hotspots[] } | C | C - dashboard
RULE: these shapes get agreed at 0:20 and never change. If a route is not ready, return hardcoded demo JSON of the same shape so nobody is blocked.

## 8. Demo Script
# | Time | What you say | What you click | Module shown | Who drives
1 | 0:00-0:20 | Meet Sunita, a daily-wage worker in Sitapur. She is eligible for six government schemes and knows about none of them. Today she would pay an agent Rs 300 to find out. | Open the deployed URL on a phone, switch language to Hindi | M5 | Presenter
2 | 0:20-0:50 | She does not search for schemes. She just shows us her documents. | Photograph the Aadhaar and income certificate -> profile fills in automatically | M2 | Person A
3 | 0:50-1:20 | Rs 42,000 a year, unclaimed. And one caste certificate away from three more schemes. Notice the warning - her name differs between Aadhaar and her passbook, which is the single biggest cause of rejection. | Schemes screen: unclaimed card, near-miss card, mismatch warning | M1, M2 | Presenter
4 | 1:20-1:50 | She cannot read the form. So she talks to it, in Hindi. | Voice form-fill, then download the filled PDF | M3 | Person A
5 | 1:50-2:10 | Her village has no network. Watch. | Turn on airplane mode, file a pothole complaint with a photo, see 'saved offline', turn network back on, watch it sync | M8, M4 | Person A
6 | 2:10-2:30 | The complaint routed itself to the right ward and department. If nobody acts in fifteen days, the app drafts the escalation. After thirty, it drafts an RTI. | Complaint timeline -> Escalate -> show the drafted letter | M4 | Person C
7 | 2:30-2:45 | To reach the tehsil office: bus route, forty minutes, fifteen rupees. And her eligibility slip verifies on a conductor's phone with no internet at all. | Transport route on the map, scan the signed QR on a second offline phone | M7 | Person C
8 | 2:45-3:00 | And the government side: this ward takes 22 days where the city average is 9. Citizen and state, same platform. | Transparency dashboard | M6 | Person C
BACKUP PLAN: record a 3-minute screen capture of this exact flow at the 2:40 mark. If the wifi dies on stage, you play the video and keep talking.